## Sprint 2
Related user story | Task Description | Developer | Initial Estimate
general task login- student | Tie the login functionality in with the rest of the system | Justin McConnell | 8 hours
General task update database | Update the database/ ERD as needed | Justin McConnell | 30 mins
general task login- student | Create seperate login for students | Justin McConnell | 4 hours
General task Separate web apps | Move the students app functionality into their own project/web app | Josh Pefinis | 1 hour
view advisment stage | Add appropriate hold messages that the owner wants | Darrius/Justin/Josh | 3 hours
inform faculty advior student has met me- web app/desktop app | Update meeting page to only allow general advisor to approve after meeting is scheudled and time is past. | Darrius Dupree | 2 hours
inform faculty advior student has met me- web app/desktop app | Link the functionality between the view and model via the controller class | Darrius Dupree | 2 hours
inform general advisor to remove hold- web app/desktop app | Update meeting page to only allow faculty advisor to approve after meeting is scheudled and time is past. | Darrius Dupree | 30 mins
General task- Update WireFrames | Update wireframes | Darrius Dupree | 30 mins
General task - Update user stories | Update userstories | Darrius Dupree | 30 mins
inform of advisor meeting with students web/desktop | Restrict approval stages to appropriate advisors | Darrius Dupree | 2 hours
schedule meeting | restrict allowing students to schedule meetings for past time | Josh Pefinis | 1 hour
Documentation | Update Class Diagram | Josh Pefinis | 1 hour